# Trot ADA – Korean Mid-Age Outreach Through Cardano-Themed Trot Shorts

Category: Community & Outreach → Content Creation
Requested: 15,000 ADA
Project Duration: 6 months

## 1. Problem Statement

Cardano has almost no visibility among Korean middle-aged and senior audiences, despite their strong presence on YouTube. Existing crypto content is not culturally tailored to them, leading to low awareness and zero onboarding. A new, familiar format is required to introduce Cardano to this demographic.

## 2. Proposed Solution

Over 6 months, produce a high-frequency series of Trot ADA YouTube Shorts, featuring a virtual Korean trot singer (ADA) performing 10–12 second clips with ADA branding (symbol + “Trot ADA”).

In parallel, publish simple Cardano educational shorts covering:

- What is ADA

- How to create a wallet

- How staking works

- Why Cardano is unique

This project leverages high-retention Korean trot culture to plant Cardano in the minds of an entirely new audience.

## 3. Why This Will Succeed

- Channel already at 750 subscribers and 500,000+ views

- +10 new subscribers daily (fast organic growth)

- Trot is Korea’s top genre among 40–70 age groups

- Short-form video ensures rapid reach with minimal cost

- Unique branding character (ADA singer) ensures memorability

## 4. 6-Month Deliverables

- 90 Trot ADA Shorts (15 per month)

- 18 Cardano educational shorts (3 per month)

- ADA-themed visual assets (overlays, motion graphics, templates)

- Monthly analytics reports (views, reach, retention, demographics)

- Final results report summarizing Cardano awareness uplift

## 5. KPIs (6-Month Targets)

- 2,000+ subscribers (3× growth in 6 months)

- 1,200,000 total views

- 15,000+ monthly viewers exposed to ADA branding

- 800+ views/month on Cardano educational shorts

- 80%+ retention

- 150–300 wallet installation or staking inquiries prompted by content

## 6. Budget – 15,000 ADA

Includes AI tools needed for daily video production.

| Item | Cost (ADA) |
| --- | --- |
| AI tools (imagine.art, InVideo, Artlist, Runway, etc.) – 6 months | 2,500 |
| Creator labor & editing | 6,000 |
| Character + graphic asset production | 2,000 |
| Community engagement + Korean outreach | 3,000 |
| Operations & contingency | 1,500 |
| Total | 15,000 ADA |

## 7. Team

Independent content creator with proven growth metrics on the Trot ADA YouTube Shorts channel.
Experience with AI tools, cultural content design, and Cardano ecosystem engagement.

## 8. Expected Impact on Cardano

This project introduces Cardano to an untapped audience—Korean mid-age users—through highly familiar content.
The approach blends entertainment with subtle ADA education, creating:

- Long-term brand awareness

- New wallet users

- Increased staking curiosity

- Stronger Cardano presence in East Asia

This is a low-cost, high-impact cultural outreach strategy for Cardano.